## Action Plan
Coronavirus Emergency Planning ¦ ACTION PLAN
ACTION ITEMS per TEAM | RESPONSIBLE PARTY | PRIORITY | STATUS | START | END | NOTES
Human Resources
Inform staff about health & medical benefits
What about outreach staff? Should people continue to meet with donors and agencies? Should we pull people off the road?
Do staff get compensated if taking on usual volunteer roles? It's almost mandatory volunteer work
Explore 3rd party labor source (alternative labor) | [5 empty] | Contact temp agencies to determine available labor in the event of an outbreak.
Practices for staff behavior o Shaking hands / greeting guest o Cleaning up after yourself o Cleaning your workspace
Establish additional process for sick leave and create a tracking process/sheet for that.
If a staff member's family member is sick or school is closed, how will this work with any new policies? | [5 empty] | For Example: If a staff member's family member is sick, then YES, this applies to our COVID-19 policy, If the school is closed, this would NOT qualify under our COVID-19 policy. Review your policies
If impacted, what's our approach to telecommuting? Who can, who can't, under what circumstance?
When do we limit face to face meetings?
Employee Emergency Contact Information
Staff Communication on COVID-19 Preparedness/Response | [5 empty] | How frequent?
Change up shifts to minimize number of people working in one place?
Volunteers
What to communicate to scheduled volunteers?
What to communicate to volunteers that schedule?
What to communicate about our needs for volunteers?
What do we communicate about safety in PR1 for volunteers?
Amelia & Paul to work together to create a unified language, re: volunteer communication?
Maybe consider adding pre-screening or self-screening questions re: travel, symptoms, etc.
Do we reassign staff to help with volunteer production?
Services, Resource Sourcing and Operations
What is the Lowest threshold of service, that we would support? Do we commit to weekly agency service? Or change to every-other week, or monthly?
Product sourcing--make special appeals to food donors about what products we want. This can be tied to a coronavirus response.
Identify baseline number of staff needed to keep operations going
Proactive staff training. Identify cross-training plan (in case we need to implement)
Maintain Agency Express! Add Supplies? Hand sanitizer?
Keep all staff working current shifts? Change up shifts to minimize number of people working in one place?
If we can't keep up with operations "as normal", what is the baseline amount of service we want to try to keep up with. Operate all programs? Cut back on some types of service? What about deliveries? Splitting shifts? Drivers--what kind of considerations?
Disaster supplies
Collaborate with other community partners
Resource Development
Keep on the calendar? Reschedule? Cancel?
Virtual fundraising event?
What else about fundraising do we need to brainstorm about?
Track resources expended related to COVID 19 for possible reimbursement later if funding sources become available
Is there an "emergency" appeal to donors? Under what circumstances?
Staff Safety
Deep clean team, supplies and process. Identify staff who would be responsible for a deep clean. | [5 empty] | Cleaning proceeding as normal with high touch areas being cleaned 4 times a day.
Communication about signage that will be developed | [5 empty] | Signage has been placed at all facility entrances.
Facility – Safety and Cleanliness practices o How to effectively clean things o Public areas o Bathrooms o Lunch room o Meeting rooms o Regular cleaning schedule during this time o Setting up cleaning stations
Staff Safety at home – how to keep yourself safe. o With Symptoms o Without Symptoms  With exacerbating circumstances (I feel fine but a family member is sick or frail)  Without exacerbating circumstances
Share transmission & incubation info
Champion Security | [5 empty] | Verify ability to continue staff and pick up additional shifts as needed
Stress Management
Safe cash, mail & food handling (food drives, etc.) | [5 empty] | Advise staff to wash hands before and after handling mail & cash.
Administrative Support
Setting Recurring Workgroup Meetings | [5 empty] | Smaller workgroups have yet to be established/created.
Track all staff hours spent working on this issue (save receipts, track expenses and create tracking system)
What is the system we're using to track all of this, to keep organized? | [5 empty] | Tentatively, Excel.
Schedule recurring meetings. | [5 empty] | Plan on meeting 2X a week for 4 weeks.
Depository for approved COVID-19 messaging, signage and other associated documents.
Finance
Sending out a project code | [5 empty] | To track expenses associated with COVID-19
Evaluate finance functions that can be completed remotely.
Track expenses for COVID-19
Tracking Hours dedicated to COVID-19??
Ensuring cleanliness when handling cash & mail. | [5 empty] | Advise staff to wash hands before and after handling mail & cash.
Marketing & Communications
Media Talking Points
Send out communication to all staff | [5 empty] | Share with staff who the area owners are, in case any questions/concerns come up
Trusted resources: CDC,…
When sending out a communication, be clear about what people need to do if they have symptoms, and what to do if there was known exposure.
General communications to the community (questions to answer) - FAQs?
Scenario Planning (ALL)
What does it look like for organization to be operating on: o Full staff with volunteers o Full staff with minimal to no volunteers o Impacted staff / no volunteers o Skeleton crew of staff / limited ability to operate specialized equipment | All
Agency Networks & Community Programs
Share signs with Agency Networks (signs that indicate what coronavirus symptoms are, and if you have any signs of a cold, to remain in vehicle. staff will bring product(s) to vehicles.
Regular Communication with Network | [5 empty] | What does this look like?
Request agencies to contact us if they change their hours of operation, business, etc. | [5 empty] | we asked agencies to reach out if they are considering changes to services or distribution models
Have agencies share with you how they're protecting themselves.
IT Updates
Telecommuting Email (how-to instructions)
VPN on Employee Laptops
Update Emergency Texting Application
Technology Available for Virtual Meetings | [5 empty] | Instructions on use, potential costs involved
Phone System Capabilities
Conference Calls/Webinars | [5 empty] | FreeConferenceCall.com

## Money Tracking
Money Tracking
PURPOSE | Date | Amount | Project Code | NOTES
Supplies
Other